## Table 1
Test Summary Report
Product Name |  |  | Level supermind
Product Description |  |  | This document outlines the testing approach, strategies, and scope for the level supermind app . It details the objectives, schedule, resource allocations, test deliverables, and reports.
Project Description |  |  | <Mission of Project> ● Conducted testing of verify the Quality of the website <Project Output> ● Test Summary Report & Evaluation ● Bug/Defect Report
|  |  | Project Type |  | Testing/Verification
Author |  |  | Shubham Giri
Total Test Cases |  |  | Functionality |  | 44
|  |  | UI/UX |  | 16
|  |  | Performance |  | 1
Test Case Status |  |  | Passed |  | 61
|  |  | Failed |  | 4
Project Duration |  |  | Start date |  | 2025-03-01
|  |  | End date |  | 2025-03-05
OPEN ISSUES | PRIORITY | ASSIGNED |  | TEST CASE ID |  | REPORTED DATE | STATUS
1 | High | QA Team |  | TC_011 |  | 2025-03-01 | Unresolved
2 | High | QA Team |  | TC_059 |  | 2025-03-01 | Unresolved
3 | High | QA Team |  | TC_060 |  | 2025-03-01 | Unresolved
4 | High | QA Team |  | TC_061 |  | 2025-03-01 | Unresolved